## Sprint 1
| Today : | 2018-06-07 |  |  |  |  | Expected Completion |  | Expected Hours |  | Notes
| Player Controller |  |  |  | : Includes Camera Controller : Smooth terrain movement : Non-Physics Based World Interactions |  | 2018-07-09 |  | 26-30 hours (1-2 days) |  | This sprint is focused on finishing the main aspects of the Player Controller so that we have a smooth controller that interact generally with the world but not investing too much time into making it perfect, things such as ledge climbing and locomotion will come into it's own sprint later down the track - For the vertical slice all of this is not improtant yet.
REF TAG | Task Name | BT 0.1 | BT 0.2 | BT 0.3 | Break Down Notes | Issues/Notes | Hours left | Completion Hours | Current Progress | Expected Completion Date | Real Completion Date
| Planning of Controller |  |  |  | Will need everything for the vertical slice of this game |  | 528 | 2-3 hours | 100% | 2018-05-16 | 2018-05-16
|  | Requirements | [6 empty] | 100%
|  | Features | [6 empty] | 100%
|  | Additionals | [6 empty] | 100%
Development Outline
| Introductory Dev Log (YT) | [5 empty] | 48 | 4-5 hours | 20% | 2018-06-05 | 2018-06-05
|  | Planning Video | [6 empty] | 100%
|  | Compiling Videos | [6 empty] | 0%
|  | Editing | [6 empty] | 0%
|  | Voice Over | [6 empty] | 30%
|  | Edit Voice Over | [6 empty] | 20%
|  | Publish | [6 empty] | 0%
| Base Movement | [5 empty] | 360 | 6 Hours | 100% | 2018-05-23 | 2018-05-25
|  | Simple Movement | [6 empty] | 100%
|  | Slope Movement | [6 empty] | 100%
|  | Efficient State Machine | [6 empty] | 100%
|  | Collision + Complex Collisions | [6 empty] | 100%
|  | Artificial Damping | [6 empty] | 100%
|  | Climbing Stairs | [6 empty] | 100%
|  | Complex Movement on Terrains (Averaging) | [6 empty] | 100%
|  | Smooth Frame Independent movemen | [6 empty] | 100%
|  | Optimised Scripts ^^ | [6 empty] | 100%
| Complex Movement | [5 empty] | 72 | 4 Hours | 10% | 2018-06-10
| Begin Modelling Player | [7 empty] | 0%
|  | Record it | [6 empty] | 0%
| Multiple Controller Sripts | [7 empty] | 100%
|  | Slope Slipping | Fix it up, it's broken | [5 empty] | 100% |  | 2018-06-03
|  | Fixing jump in consistancies |  |  | Remove from Updt |  |  |  | 100%
|  | Jump Hold Power |  |  | Un-Needed
|  | Crouching/Sprinting |  |  | Un-Needed
|  | Ladder Climbing System |  |  | Custom Controller at Collider |  |  |  | 10% | 2018-06-05
|  | Ledge Climbing System |  |  | Custom Controller at Collider |  |  |  | 10% | 2018-06-06
Integratingn Animations
|  | Strafing | [6 empty] | 100%
[7 empty] | 120 | 50 | 20% | 2018-06-12
IN ORDER
| Player Error Correcting |  |  |  | The player fallst through the ground, so you need to check and fix it… | The player snaps through the floor sometimes, so check if input is affecting the instantaneous velocity which is measured each frame | 192 |  | 0% | 2018-06-15
| Procedural Animation System | Setting Up Mecanim | Mecanim Masks+Codical Enabling/Disabling | Script Disabling/Enabling + Custom Animation Flows When Needed |  | The procedural part of this will come when we finish the IK system and things like pivoting can be done through curves and rotating the pelvis and transitioning and changing to backward walk etc.. | 120 |  | 75% | 2018-06-12
| Procedural Walking System | Forward/Turn Backward/Strafing | Blend Tree, Controlled by Script | Velocity changes animations + Different Speeded Animations (Walk and Run) | Fix Strafing Animation Later Create Pivoting Begin IK System | The pivoting system is just proceudrally done for now, it isn't perfect but it's fine. It works for now, the next thing I have to do now is the IK System. I cannottt wait. FABRIK here we come. | 120 |  | 75% | 2018-06-12
| Building IK System | Trying out current IK System with mecanim masks (Foot and Wrists) | Building own one using the proper algorithm and constraints etc, with an editor | Making it work with all animations and proper foot correction etc with optimisation |  | The IK system needs to be very flexible, with an editor that can attach bones, etc. New menu's and using normals to rotate the feet and then lift up the feet. Nice. | 120 |  | 0% | 2018-06-12
| Ledge Detection and Climbing w/ Animations | Will take a closer look at this when the prior movmeent system is completed | Parkour System/Ladder Climbing |  |  | Using the blend trees and offsets to allow you to grab onto ledges, new controller. | 120 |  | 0% | 2018-06-12
2018-06-12
| Optimisation / Testing |  |  |  |  | This is important to make sure that the player isn't using up too many resources, make sure you disable features on the update when they aren't being used etc… | 120 |  |  | 2018-06-12
[5 empty] | The end of this section also requires - An animation for all states, and independent of movement blending between states procedurally using curves. Learn about masks and seperating upper/Lower body movement. | By the end of this section you need, a simple walking animation that is smooth with pivoting and foot ik implemented with FABRIK. It also needs to have a rudimentary ledge climbing system that can hold onto ledges and hoist yourself up. This also needs to be displayed in a video, of him climbing up a ledge.
| Camera System | [5 empty] | 1608 | 4 hours |  | 2018-04-01
|  | ASSASINS CREED SYSTEM | [6 empty] | 100%
Smooth Frame independent Camera Follow
|  | Player Orbit | [6 empty] | 100%
|  | Camera Collisions | [6 empty] | 0%
Smart Algorithms to Detect Player Detectability by User
Disable and Enable Objects
Camera TPS Aim Switching
Optimised Scripts ^^
| Aiming System |  |  |  | This does not include the actual physics of the bow and arrow, this just includes the aiming features |  |  | 4-5 Hours |  | 2018-04-05
Over the shoulder aimaing
Auto Locking
Crosshair placement
Crosshair locking
Crosshair target changing
Accurate Raycasting
Dynamic IK (Unity IBK)
Aim Movement (Change)
Proper Zooming
| Optimisation / Testing | [6 empty] | 2-3 Hours |  | 2018-04-08
Testing on complex terrains
Levels w/ Stairs, Slopes / Complex Falls etc..
Profiler Tests (Deep Profiler)
No Unrequired Update Functions
Organise the Scripts and Exposed Public Variabls
Formulas:
Hours left = ABS(DAYS(TODAY(), [Expected Completion Date])*24)

## Current Tasks
Procedural Movement System | Notes | Hours | Prog | 2018-06-07 | Notes | Hours | Prog | 2018-06-08 | Notes | Hours | Prog
Plan out the camera system |  | 0.2 | 100% | Expected Result | https://www.youtube.com/watch?v=YixF6p7YVeU
How to make it realistic | Using lag, increased fov, speed, motion blur, auto movement… | 0.2 | 100%
Implement the camera orbitting w/ Lag |  | 1 | 100%
Changing the movement system relative to camera |  | 0.2 | 100%
Adding discrepancies for big movement changes |  | 0.2 | 100%
Making the animations work while turning around |  | 0.5 | 100%
Pivoting System for Direction Changes | You will have to create individual ones that make sense | 1 | 100%
Fix the player clipping through the ground |  |  | 0%
| Begin the IK System | 2.3
Planning how FABRIK will work |  | 0.5 | 0%
Planning out the editor and how to make it comprehensicve |  | 0.1 | 0%
What functions and limitations the system will have |  | 0.1 | 0%
| Begin Writing the IK System | 2.3

## Sprint Journal
AJAY VENKAT
|  | NEFARIOUS | JOURNAL
|  |  | TOTAL W : | 0
SPRID | DATE | TODO | NOTES | JOURNAL | Issues | HOURS
| 2018-01-28 |  | Well First I am going to start off by creating a bumper sphere using the rigidbody to check if the collisions are registered. For jumping I will be using the inbuilt add force for jumping so it doesn’t get messy. Unity has inbuilt physics for a reason, they are the leading Physics experts okay, so if you use the system right and use it alongside your systems then you can have a good experience with player control, you just have to make sure your motor has the ability to turn of the rigid body without you having to access the component through the gameobject. |  |  | 1
| 2018-01-29 |  | Today I have decided to fully harness the potential of the Unity Editor using the rigibody system. In my movement using the motor I will be using the rigibody.position element in order to make sure that the rbody always knows where I am at so I won't be getting collider issues throughout the game. I will also make sure that the gravity and phsyics is fully under my control whenever i need it to be. |  |  | 2
| 2018-05-30 |  | Okay so I would like to make an entry regarding quality of the player controller, this is a sprint that we can refer back to later when we need to right. Because for the vertical slice of the game we don't need the most beautiful player controller. We just need to get started on the game and I have already finished the basics of the controller. So what is the next aspect of the vertical slice we have to focus on. Go through the final game plan and make a new document for the vertical slice, becasue that is the best way to understand if the playe style of this game will actually work or not. So let's do some more plannign yayyaya | Once I have all the base systems working then I will get into the real integration of the systems in a proper way and how it all unfold throughout the game, how the player will know what to do etc… Guides throughout the game, based on the events of what is happening. I belive based on the subtractive design theory, inventory, crafting and world destruction are not required for our game as we are a more fighting and stealth action game, so that is good indeed.
| Game Clarification | Basic synopsis of the game -> You're getting attacked, so you're sent out into a lively world filled with enemies with your friend. Survive and use your tactical fighting skills to take down the enmy and successfully infilitrate the enemy base and place the bomb. Many things may happen, bomb getting stolen, etc.. But the combat is the most important part - like csgo combat with very smart npcs. Fully open world - the world needs to be interactive and it actually needs to contribute to the game play with many livelness around the palce. But all of this can be taken into consideration once the actual systems of the game are complete which I am working towards now anyway. So once that is done we will worry about this. But that's the basics of the game. | IN the final document I keep refering to a story, well there is no story except for the fact there will be a overall mission - deliver the bomb and kill the enemy. The rest is up to you and your friend. Story is conveyed through the secrets you can find in the world, the interaction with your friend and just the environment. No in game dialogue etc.. Just a guiding box sometimes if you need it or signs here and there helping you out on where to go. There is also no survival aspect to a point, there will be enemies littered around the place - you jsut have to explore the world, kill enemies, loot, get stronger, take care of eachother, stealth your way around a massive open world while surviving. Then there are all the villages, clans, robbers, theives in the middle that interfere with you + wild animals and the epic beasts that you will have ti fight. | The fighting needs to be the most gratifying and fun part of the game, no stupid fighting of spamming buttons, actual tactical fighting using your friend as your guidance. Throwing smokes, confusing the enemy. Sneaking up on him, taking long arrow shots. ITS THAT PART OF THE GAME THAT WILL MAKE IT SPECIAL. But don't be mistaken, just because there is no explicity story, doesnt mean there isnt internal story of why the war, what happened, previous back stories blah blah blah all secrets throughout the world design. THis is whery importanttttt. Okay so don't forget but in essence this is an open world stealth action combat game. So sick. I KNOW for sure for sure what i am doing for this game now. So finish the systems, do a vertical slice with all the features, put them together, polish and then stitch all the features, designs into one big level and optimise and vioalaaaaaa -- game.
| Gameplay Clarification | Okay so I am working on the player controller now, so I have the ladder system ready but I will not be working on that now. I need a sustainable method of creating and deploying animations. I also need to use this for the ledge system where it will all be dynamic. Walls will be auto processed for grabbing points etc..Then using procedural animations you can scale the wall | I don't actually want to mess with the project file when I am doing player tests so I have deleted it out | Okay so I am currently working on getting the mecanim to work with a base player, that can move in the way that assasins creed can. The first step is to get the animations in so that the blend tree can do it's magic. Once that is complete I will work on the camera controller, then it will be all the ledge climbing system. I will have to wait until next weekend before I can really kick this off again tho......
| Camera Clarification |  | So there are two main types of cameras that I am contemplating and one is where you are close up to the player behind and can orbit him like in Assasins Creed or the same system but further away because low poly always looks better when it is further away but then it takes that open world sense out of it. It's all up to you but at the end of the day you have to pick between what looks good and what makes the game feel better. If you can get an open world sense with the camera quite backed up then I reccomend you do that but otherwisse stay away from it I guess. maehhh
| Animation Clarification | Creating the sample animations is so much harder than I expected, I might just use built in mocap data for experimentation and if it's good why not just keep it then… | So the way I will be doing animations is like this (final) - I will be animating by hand most of the animations that are required in my system. The system being only forward has movement aniimations, but turning around has a rotation turn right or left and this will be detected by input and the severety of the turn will be also decided by input. | You will use blend trees and 2D trees in order to blend between correct animations and I will use masks in the right places in order to merge aninations together. Because Unity has very nice handling of this, but if it is not satisfactory at anypoint then I will be redesigning this system but it's not important for now. | Using the masks and other techniques I will include IK into the procedure as well so that I can automatically change any limbs in LateUpdate() and awesome stuff like that. So Mecanim is very powerful so we will continue to use that for the movement system.
| Anim Clarif 2 |  | There are still a lot of errors some of which include - : THERE MUST BE TRANSITION STATES BETWEEN THE ANIMATIONS : FIX THE STRAFING : SEPARATE ANIMATIONS FOR DIAGONAL MOVEMENT : IDLE POSE NEEDS TO BE CALLED ON DIFFERENT | https://www.youtube.com/watch?v=zy9E-w4QM2o PIVOTING
|  |  | Let me get this straight, this movement system that I am building is just a build up of how I would manage it when I implement it into my game. So the animations don't have to be perfect. I just want to implement The assasins creed movement system with IK and animations inside this game. It's important. | Now this is all just really building up to finishing the player system off, so I will finish the camera system and make that work all nicely with FOV transofrmations etc… It will all be very ncie. Then I will get ledge climbing and ladder climbing to work seamlessly. Then I will get a quick parkour system running with smooth animations by then

## Sprint 2
| Today : | 2018-06-07 |  |  |  | Expected Completion |  | Expected Hours
NPC Development
REF TAG | Task Name | BT 0.1 | BT 0.2 | BT 0.3 | Break Down Notes | Completion Hours | Current Progress | Expected Completion Date | Real Completion Date
NPC System
§ Behaviour Editor
§ Custom Regional Path finding
§ Build upon dialogue system
§ Designing the AI States and beginning proceduralised states
§ Writing the complex + dynamic combat system.
§ Realistic NPC (Friend)
§ Writing the communication system what each hand signal means and how your friend will react to each one.

## IssueLogs
Issue Log | Fix | Perc %
Slope Changes Direction and Breaks Animations
There is no pivotting