## Sprint 1
| Today : | 2018-06-03 |  |  |  | Expected Completion |  | Expected Hours |  | Notes
| Player Controller |  |  |  | : Includes Camera Controller : Smooth terrain movement : Non-Physics Based World Interactions | 2018-04-08 |  | 26-30 hours (1-2 days) |  | This sprint is focused on finishing the main aspects of the Player Controller so that we have a smooth controller that interact generally with the world but not investing too much time into making it perfect, things such as ledge climbing and locomotion will come into it's own sprint later down the track - For the vertical slice all of this is not improtant yet.
REF TAG | Task Name | BT 0.1 | BT 0.2 | BT 0.3 | Break Down Notes | Hours left | Completion Hours | Current Progress | Expected Completion Date | Real Completion Date
| Planning of Controller |  |  |  | Will need everything for the vertical slice of this game | 432 | 2-3 hours | 100% | 2018-05-16 | 2018-05-16
|  | Requirements | [5 empty] | 100%
|  | Features | [5 empty] | 100%
|  | Additionals | [5 empty] | 100%
Development Outline
| Introductory Dev Log (YT) |  |  |  |  | 48 | 4-5 hours | 20% | 2018-06-05 | 2018-06-05
|  | Planning Video | [5 empty] | 100%
|  | Compiling Videos | [5 empty] | 0%
|  | Editing | [5 empty] | 0%
|  | Voice Over | [5 empty] | 30%
|  | Edit Voice Over | [5 empty] | 20%
|  | Publish | [5 empty] | 0%
| Base Movement |  |  |  |  | 264 | 6 Hours | 100% | 2018-05-23 | 2018-05-25
|  | Simple Movement | [5 empty] | 100%
|  | Slope Movement | [5 empty] | 100%
|  | Efficient State Machine | [5 empty] | 100%
|  | Collision + Complex Collisions | [5 empty] | 100%
|  | Artificial Damping | [5 empty] | 100%
|  | Climbing Stairs | [5 empty] | 100%
|  | Complex Movement on Terrains (Averaging) | [5 empty] | 100%
|  | Smooth Frame Independent movemen | [5 empty] | 100%
|  | Optimised Scripts ^^ | [5 empty] | 100%
| Complex Movement |  |  |  |  | 168 | 4 Hours | 10% | 2018-06-10
| Begin Modelling Player | [6 empty] | 0%
|  | Record it | [5 empty] | 0%
| Multiple Controller Sripts | [6 empty] | 100%
|  | Slope Slipping | Fix it up, it's broken |  |  |  |  | 100% |  | 2018-06-03
|  | Fixing jump in consistancies |  |  | Remove from Updt |  |  | 100%
|  | Jump Hold Power |  |  | Un-Needed
|  | Crouching/Sprinting |  |  | Un-Needed
REQUIRED |  | Ladder Climbing System |  |  | Custom Controller at Collider |  |  | 10% | 2018-06-05
REQUIRED |  | Ledge Climbing System |  |  | Custom Controller at Collider |  |  | 10% | 2018-06-06
|  | Strafing | [5 empty] | 100%
Fix any issues / cross platform
| Camera System |  |  |  |  | 1512 | 4 hours |  | 2018-04-01
Find out how these systems work…
Smooth Frame independent Camera Follow
Player Orbit
Camera Collisions
Smart Algorithms to Detect Player Detectability by User
Disable and Enable Objects
Camera TPS Aim Switching
Optimised Scripts ^^
| Aiming System |  |  |  | This does not include the actual physics of the bow and arrow, this just includes the aiming features | 1416 | 4-5 Hours |  | 2018-04-05
Over the shoulder aimaing
Auto Locking
Crosshair placement
Crosshair locking
Crosshair target changing
Accurate Raycasting
Dynamic IK (Unity IBK)
Aim Movement (Change)
Proper Zooming
| Optimisation / Testing |  |  |  |  | 1344 | 2-3 Hours |  | 2018-04-08
Testing on complex terrains
Levels w/ Stairs, Slopes / Complex Falls etc..
Profiler Tests (Deep Profiler)
No Unrequired Update Functions
Organise the Scripts and Exposed Public Variabls
Formulas:
Hours left = ABS(DAYS(TODAY(), [Expected Completion Date])*24)
Hours left = DAYS(TODAY(), [Expected Completion Date])*24

## Sprint 2
| Today : | 2018-06-03 |  |  |  | Expected Completion |  | Expected Hours
NPC Development
REF TAG | Task Name | BT 0.1 | BT 0.2 | BT 0.3 | Break Down Notes | Completion Hours | Current Progress | Expected Completion Date | Real Completion Date
NPC System
§ Behaviour Editor
§ Custom Regional Path finding
§ Build upon dialogue system
§ Designing the AI States and beginning proceduralised states
§ Writing the complex + dynamic combat system.
§ Realistic NPC (Friend)
§ Writing the communication system what each hand signal means and how your friend will react to each one.

## Sprint Journal
AJAY VENKAT
|  | NEFARIOUS | JOURNAL
|  |  | TOTAL W : | 0
SPRID | DATE | TODO | NOTES | JOURNAL | Issues | HOURS
| 2018-01-28 |  | Well First I am going to start off by creating a bumper sphere using the rigidbody to check if the collisions are registered. For jumping I will be using the inbuilt add force for jumping so it doesn’t get messy. Unity has inbuilt physics for a reason, they are the leading Physics experts okay, so if you use the system right and use it alongside your systems then you can have a good experience with player control, you just have to make sure your motor has the ability to turn of the rigid body without you having to access the component through the gameobject. |  |  | 1
| 2018-01-29 |  | Today I have decided to fully harness the potential of the Unity Editor using the rigibody system. In my movement using the motor I will be using the rigibody.position element in order to make sure that the rbody always knows where I am at so I won't be getting collider issues throughout the game. I will also make sure that the gravity and phsyics is fully under my control whenever i need it to be. |  |  | 2
| 2018-05-30 |  | Okay so I would like to make an entry regarding quality of the player controller, this is a sprint that we can refer back to later when we need to right. Because for the vertical slice of the game we don't need the most beautiful player controller. We just need to get started on the game and I have already finished the basics of the controller. So what is the next aspect of the vertical slice we have to focus on. Go through the final game plan and make a new document for the vertical slice, becasue that is the best way to understand if the playe style of this game will actually work or not. So let's do some more plannign yayyaya | Once I have all the base systems working then I will get into the real integration of the systems in a proper way and how it all unfold throughout the game, how the player will know what to do etc… Guides throughout the game, based on the events of what is happening. I belive based on the subtractive design theory, inventory, crafting and world destruction are not required for our game as we are a more fighting and stealth action game, so that is good indeed.
| Game Clarification | Basic synopsis of the game -> You're getting attacked, so you're sent out into a lively world filled with enemies with your friend. Survive and use your tactical fighting skills to take down the enmy and successfully infilitrate the enemy base and place the bomb. Many things may happen, bomb getting stolen, etc.. But the combat is the most important part - like csgo combat with very smart npcs. Fully open world - the world needs to be interactive and it actually needs to contribute to the game play with many livelness around the palce. But all of this can be taken into consideration once the actual systems of the game are complete which I am working towards now anyway. So once that is done we will worry about this. But that's the basics of the game. | IN the final document I keep refering to a story, well there is no story except for the fact there will be a overall mission - deliver the bomb and kill the enemy. The rest is up to you and your friend. Story is conveyed through the secrets you can find in the world, the interaction with your friend and just the environment. No in game dialogue etc.. Just a guiding box sometimes if you need it or signs here and there helping you out on where to go. There is also no survival aspect to a point, there will be enemies littered around the place - you jsut have to explore the world, kill enemies, loot, get stronger, take care of eachother, stealth your way around a massive open world while surviving. Then there are all the villages, clans, robbers, theives in the middle that interfere with you + wild animals and the epic beasts that you will have ti fight. | The fighting needs to be the most gratifying and fun part of the game, no stupid fighting of spamming buttons, actual tactical fighting using your friend as your guidance. Throwing smokes, confusing the enemy. Sneaking up on him, taking long arrow shots. ITS THAT PART OF THE GAME THAT WILL MAKE IT SPECIAL. But don't be mistaken, just because there is no explicity story, doesnt mean there isnt internal story of why the war, what happened, previous back stories blah blah blah all secrets throughout the world design. THis is whery importanttttt. Okay so don't forget but in essence this is an open world stealth action combat game. So sick. I KNOW for sure for sure what i am doing for this game now. So finish the systems, do a vertical slice with all the features, put them together, polish and then stitch all the features, designs into one big level and optimise and vioalaaaaaa -- game.