## Sprint 1
| Today : | 2018-05-20 |  |  |  | Expected Completion |  | Expected Hours |  | Notes
| Player Controller |  |  |  | : Includes Camera Controller : Smooth terrain movement : Non-Physics Based World Interactions | 2018-04-08 |  | 26-30 hours (1-2 days) |  | This sprint is focused on finishing the main aspects of the Player Controller so that we have a smooth controller that interact generally with the world but not investing too much time into making it perfect, things such as ledge climbing and locomotion will come into it's own sprint later down the track - For the vertical slice all of this is not improtant yet.
REF TAG | Task Name | BT 0.1 | BT 0.2 | BT 0.3 | Break Down Notes | Completion Hours | Current Progress | Expected Completion Date | Real Completion Date
| Planning of Controller |  |  |  | Will need everything for the vertical slice of this game | 2-3 hours | 100% | 2018-05-16 | 2018-05-16
|  | Requirements |  |  |  |  | 100%
|  | Features |  |  |  |  | 100%
|  | Additionals |  |  |  |  | 100%
Development Outline
| Introductory Dev Log (YT) |  |  |  |  | 4-5 hours | 20% | 2018-05-16 | 2018-05-18
|  | Planning Video |  |  |  |  | 100%
|  | Compiling Videos |  |  |  |  | 0%
|  | Editing |  |  |  |  | 0%
|  | Voice Over |  |  |  |  | 30%
|  | Edit Voice Over |  |  |  |  | 20%
|  | Publish |  |  |  |  | 0%
| Base Movement |  |  |  |  | 6 Hours | 5% | 2018-05-23
Simple Movement
Slope Movement
Efficient State Machine
Collision + Complex Collisions
Artificial Damping
Climbing Stairs
Complex Movement on Terrains (Averaging)
Smooth Frame Independent movemen
Optimised Scripts ^^
| Complex Movement |  |  |  |  | 4 Hours |  | 2018-05-28
Slope Slipping
Jump Hold Power
Crouching/Sprinting
Sliding (Collider Change)
Strafing
| Camera System |  |  |  |  | 4 hours |  | 2018-04-01
Smooth Frame independent Camera Follow
Player Orbit
Camera Collisions
Smart Algorithms to Detect Player Detectability by User
Disable and Enable Objects
Camera TPS Aim Switching
Optimised Scripts ^^
| Aiming System |  |  |  | This does not include the actual physics of the bow and arrow, this just includes the aiming features | 4-5 Hours |  | 2018-04-05
Over the shoulder aimaing
Auto Locking
Crosshair placement
Crosshair locking
Crosshair target changing
Accurate Raycasting
Dynamic IK (Unity IBK)
Aim Movement (Change)
Proper Zooming
| Optimisation / Testing |  |  |  |  | 2-3 Hours |  | 2018-04-08
Testing on complex terrains
Levels w/ Stairs, Slopes / Complex Falls etc..
Profiler Tests (Deep Profiler)
No Unrequired Update Functions
Organise the Scripts and Exposed Public Variabls

## Sprint 2
| Today : | 2018-05-20 |  |  |  | Expected Completion |  | Expected Hours
Projecct Development
REF TAG | Task Name | BT 0.1 | BT 0.2 | BT 0.3 | Break Down Notes | Completion Hours | Current Progress | Expected Completion Date | Real Completion Date
| Story Document |  |  |  |  | 3 | 10%
|  | Story Progressoin |  |  |  | 1 | 5%
|  | Character Progression |  |  |  | 1 | 5%
|  | Possible Complications |  |  |  | 1 | 5%
| Gameplay Elements Required |  |  |  |  | 2 | 0%
|  | Design Elements |  |  |  | 1 | 0%
|  | Implementation |  |  |  | 1 | 0%

## Sprint Journal
AJAY VENKAT
|  | NEFARIOUS | JOURNAL
|  |  | TOTAL W : | 0
SPRID | DATE | TODO | NOTES | JOURNAL | Issues | HOURS
| 2018-01-28 |  | Well First I am going to start off by creating a bumper sphere using the rigidbody to check if the collisions are registered. For jumping I will be using the inbuilt add force for jumping so it doesn’t get messy. Unity has inbuilt physics for a reason, they are the leading Physics experts okay, so if you use the system right and use it alongside your systems then you can have a good experience with player control, you just have to make sure your motor has the ability to turn of the rigid body without you having to access the component through the gameobject. |  |  | 1
| 2018-01-29 |  | Today I have decided to fully harness the potential of the Unity Editor using the rigibody system. In my movement using the motor I will be using the rigibody.position element in order to make sure that the rbody always knows where I am at so I won't be getting collider issues throughout the game. I will also make sure that the gravity and phsyics is fully under my control whenever i need it to be. |  |  | 2